## JOBS
Priority 0=Standard budget item
Priority 1=Essential
Priority 2=Important
Priority 3=Very useful,and quick & low cost (<£10),could omit or defer
Priority 4=Very useful but significant effort or cost,could omit or defer
Priority 5=Nice to have but could defer
| SCHEDULED MAINTENANCE |  | PRIORITY | TYPE | ORGANISER | BUDGET | TOTAL
#REF! | Acquire water filter cartridges (6 monthly replace't) | Electrical | 0 | Acquistion | DK | 30 | 30
#REF! | Remove all surplus materials and food etc |  | 0 | Cleanup | DF | 0 | 30
#REF! | Check compliance standards for 2006 and begin jobs |  | 0 | Compliance | DA | 0 | 30
| Check and adjust bow & stern fenders; 2005 - provide additional button on rear fender |  | 0 | Rope work | AK | 40 | 70
1 | New end of trip sheets | General | 0 | Standard | CJ | 0 | 70
#REF! | Replace batteries as required - 2005 esp. starter battery |  | 0 | Standard | DA | 40 | 110
| Service engine now & mid season (air, oil & fuel filters, engine & gear oil, valve clearances) |  | 0 | Standard | DA via Dealer | 400 | 510
1 | Co-ordinate clean up after working w/e | General | 0 | Standard | DF | 80 | 590
2 | Working w/e food | General | 0 | Standard | DF | 100 | 690
#REF! | winterising/dewinterising |  | 0 | Standard | DK | 30 | 720
#REF! | Re-stock first aid kit | Interior | 0 | Standard | HA | 5 | 725
#REF! | Blanket cleaning & Pillow | General - end | 0 | Standard | PB | 80 | 805
| Clean Shower sump (bucket) & deal with leaking shower pump (check shower refurbishment item) |  | 0 | Standard | PB | 10 | 815
1 | Fit new front door |  | 1 | Carpentry | CJ | 10 | 825
#REF! | Separate the gas pipe to boiler and cable in roof |  | 1 | Compliance | DK | 0 | 825 | 0
| Solder fixings on services battery to meet compliance & resolder starter battery connector |  | 1 | Compliance | PB | 10 | 835
| Drain and clean diesel tank |  | 1 | Engineering | DB |  | 835
| Check/replace flexible exhaust coupling |  | 1 | Engineering | PB | 30 | 865
| Repair and test alternators |  | 1 | Engineering | PB | 50 | 915
| Modify alternator system to double belt operation |  | 1 | Engineering | PB | 50 | 965
| Service fan on inverter |  | 1 | Engineering | PB | 0 | 965
| Deal with engine header tank overflow problem |  | 1 | Engineering | PB | 30 | 995
| Repair stern tube (arrange with yard) |  | 1 | Engineering | PB | 400 | 1395
| Deal with central heating leak in boiler compartment |  | 1 | plumbing | DK |  | 1395
| Replace broken window in rear cabin |  | 1 | Windows | CJ | 5 | 1400 | 0
#REF! | Fix window leaks - front starboard and front loo |  | 1 | Windows | CJ/AS | 10 | 1410
| Replace tools and spanners |  | 2 | Acquistion | PB | 130 | 1540
| Fix diesel leak on fuel hose(s) |  | 2 | Engineering | PB | 0 | 1540
| Adjust throttle for speedier engagement of reverse gear |  | 2 | Engineering | PB | 0 | 1540
| Provide hidden area under DRK's bunk |  | 2 | Engineering | PB | 40 | 1580
| Check for water under floor and pump out as necessary |  | 2 | Floor | DA/DB | 0 | 1580
| Replace any weak floor areas |  | 2 | Floor | DA/DB | 20 | 1600
| Trim matting on steps to improve draining/cleaning |  | 2 | Floor | DB |  | 1600
| Review success of rubber matting in place of new boards |  | 2 | Floor | DB |  | 1600
#REF! | Repair damaged cushion |  | 2 | General engineering | DA | 5 | 1605
| Seal or replace rear loo tank (contract out) |  | 2 | loo | AK | 200 | 1805
| Service loos including replacement of seals and plugs |  | 2 | loo | DK |  | 1805
| De-winterise and refurbish water pump |  | 2 | plumbing | DK | 30 | 1835 | 0
| Fit drainage tray under water pump |  | 2 | plumbing | DK | 10 | 1845
#REF! | Repair catches & ease wardrobe doors |  | 3 | Carpentry | AS | 10 | 1855
| Secure top of door frame in rear cabin |  | 3 | Carpentry | AS | 0 | 1855
| Provide more hooks in rear lobby area |  | 3 | Carpentry | AS | 5 | 1860 | 0
| Repair torn insulation jacket on boiler |  | 3 | General engineering | AS | 5 | 1865
| Install burglar alarm or other crime prevention measures |  | 3 | General engineering | DA | 0 | 1865
| Obtain replacement front right hand burner for cooker |  | 3 | General engineering | DF | 20 | 1885
1 | Clean and repaint inside of rear gas locker |  | 3 | Painting | DF | 10 | 1895
| Clean roof |  | 3 | Painting | DiJ | 5 | 1900 | 0
1 | Add bellows to exhaust/engine link |  | 4.1 | Engineering | PB | 30 | 1930
#REF! | Provide/move light to be over mirror in front loo |  | 4.1 | Lighting | AK | 10 | 1940
| Continue lighting replacement programme |  | 4.1 | Lighting | AK | 50 | 1990
| Clean battery holding frames, de-rust and repaint |  | 4.2 | Painting | DB | 0 | 1990
| Sugar soap state room and re-varnish |  | 4.3 | Painting | DF&PF | 0 | 1990
| Sugar soap loo ceilings and re-varnish |  | 4.3 | Painting | DF&PF | 0 | 1990
| Re-varnish window frames as necessary |  | 4.3 | Painting | DF&PF | 0 | 1990
| Re-install Chargemaster |  | 4.4 | Engineering | PB | 0 | 1990
| Upgrade inverter & possibly charge control (contract?) |  | 4.4 | Engineering | PB | 1000 | 2990 | 0
| Arrange a contract to refurbish and re-plumb shower compartment |  | 4.5 | Refurbishment | AS | 2000 | 4990
| Re-fit/re-model steps to improve ease of removal |  | 5 | Engineering | PB | 0 | 4990
| Paint external surfaces not dealt with in 2004 |  | 5 | Painting | DB | 0 | 4990
| Sand down and repaint or replace side hatch door. |  | 5 | Painting | DB | 40 | 5030
| Touch up paint on roof, gunnels, front well |  | 5 | Painting | DF,PF,DiJ | 0 | 5030
| Wire brush metal roof vent covings, de-rust and re-paint |  | 5 | Painting | DiJ | 0 | 5030
| Replace worn front rope |  | 5 | Rope work | AK | 50 | 5080 | 0
| OVERALL TOTAL |  |  | to priority | 4.9 | 4990
| BUDGETED TOTAL | to priority |  |  |  | 5080 |  | 0
|  |  | 5.0 |  |  | Priority
<5.0

## Budget
BUDGET
Priority 0=Standard budget item
Priority 1=Essential
Priority 2=Important
Priority 3=Very useful,and quick & low cost (<£10),could omit or defer
Priority 4=Very useful but significant effort or cost,could omit or defer
Priority 5=Nice to have but could defer
Do Jobs to Priority | 4.9
Estimated OutGoings |  | Estimated Income
Moorings Insurance & Licence | 2800 | Shares | 3600
Scheduled Maintenance | 4990 | NPs | 1000
Account Charges | 0 | Trip/Daily income | 320
Unplanned | 800
Gifts/donations | 50
Year Outgoings | 8640 | Year Income | 4920
Special Projects
2005 Floating Fund | 2809 | 2004 Floating Fund | 6529
Gross Outgoings | 11449 | Gross income | 11449
Winter Moorings | 450 | NP rate | 10
Occasional moorings | 1500 | Trip Charge surplus (* 1) | 120
Insurance | 250 | Daily Charge surplus (*2) | 200
Licence | 600 | Share | 400
2800
*1 assumes trip charge unchanged @ £20 |  | No. of Participants | 9
*2 assumes day charge unchanged @ £10/£13 |  | Number of NP days | 100